## Sheet1
Task | Assigned To | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5
|  | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
|  | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S
Implement backend infrastructure
Implement database and related operations | bar: Week 1 19 S to Week 2 1 S
Implement data classes (e.g. Book, Borrow) | bar: Week 1 23 T to Week 4 15 S
Implement utility classes | bar: Week 2 29 W to Week 5 19 W
Implement common functionality
Implement login | bar: Week 3 7 F to Week 3 8 S; Week 4 11 T to Week 4 13 T
Implement account registration | bar: Week 3 7 F to Week 3 8 S; Week 4 11 T to Week 4 13 T
Implement profile update tab | bar: Week 1 23 T to Week 3 3 M
Implement notifications tab | bar: Week 1 23 T to Week 4 10 M
Implement tests | All | bar: Week 4 12 W to Week 5 22 S
Task 1 (Student/Staff)
Implement Task 1 UI | bar: Week 1 23 T to Week 2 28 T
Implement Task 1.2 | bar: Week 2 27 M to Week 2 31 F
Implement Task 1.3 | bar: Week 2 1 S to Week 3 6 T
Implement Honors Task 1.1 | bar: Week 4 9 S to Week 5 19 W
Implement Honors Task 1.2 | bar: Week 4 14 F to Week 5 18 T
Task 2 (Author)
Implement Task 2 UI | bar: Week 1 21 T to Week 2 26 S
Implement Task 2.2 | bar: Week 1 25 S to Week 2 31 F
Implement Task 2.3 | bar: Week 2 29 W to Week 3 3 M
Implement Task 2.4 | bar: Week 3 4 T to Week 4 9 S
Implement Honors Task 2.1 | bar: Week 3 8 S to Week 5 21 F
Task 3 (Librarian)
Implement Task 3 UI | bar: Week 1 23 T to Week 2 26 S
Implement Task 3.2 | bar: Week 1 25 S to Week 2 29 W
Implement Task 3.3 | bar: Week 2 30 T to Week 2 1 S
Implement Task 3.5 | bar: Week 3 2 S to Week 3 5 W
Implement Task 3.6 | bar: Week 3 5 W to Week 3 8 S
Implement Honors Task 3.1 | bar: Week 3 8 S to Week 4 12 W
Implement Honors Task 3.2 | bar: Week 4 11 T to Week 5 18 T