## Sprint 2 burndown chart
Sprint Tasks (Sprint Backlog) | Week 1 Oct. 20-24 | Week 2 Oct. 27-31 | Week 3 Nov. 3-7 | Week 4 Nov. 10-14 | Week 5 Nov. 17-21
Implement database and related operations | 12 | 10 | 5 | 1 | 0
Implement data classes (e.g. Book, Borrow) | 6 | 4 | 2 | 0 | 0
Implement utility classes | 4 | 4 | 1 | 0 | 0
Implement login | 2 | 2 | 2 | 0 | 0
Implement account registration | 2 | 2 | 2 | 0 | 0
Implement profile update tab | 2 | 2 | 2 | 0 | 0
Implement notifications tab | 5 | 5 | 5 | 2 | 0
Implement tests | 0 | 0 | 0 | 8 | 0
Implement Task 1 UI | 3 | 1 | 0 | 0 | 0
Implement Task 1.2 | 6 | 6 | 6 | 2 | 0
Implement Task 1.3 | 6 | 6 | 6 | 3 | 0
Implement Honors Task 1.1 | 8 | 8 | 8 | 6 | 0
Implement Honors Task 1.2 | 1.5 | 1.5 | 1.5 | 0 | 0
Implement Task 2 UI | 3 | 1 | 0 | 0 | 0
Implement Task 2.2 | 6 | 2 | 0 | 0 | 0
Implement Task 2.3 | 2 | 6 | 2 | 0 | 0
Implement Task 2.4 | 0 | 2 | 6 | 2 | 0
Implement Honors Task 2.1 | 0 | 0 | 4 | 8 | 6
Implement Task 3 UI | 3 | 1 | 0 | 0 | 0
Implement Task 3.2 | 6 | 4 | 0 | 0 | 0
Implement Task 3.3 | 2 | 4 | 0 | 0 | 0
Implement Task 3.5 | 0 | 2 | 2 | 0 | 0
Implement Task 3.6 | 0 | 0 | 2 | 2 | 0
Implement Honors Task 3.1 | 0 | 0 | 6 | 6 | 0
Implement Honors Task 3.2 | 0 | 0 | 0 | 6 | 6
Total hours | 79.5 | 73.5 | 62.5 | 46 | 12